## Sheet1
Sprint Backlog Template
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Create Accounts and Authorize
Create database |  |  |  | 7 | 5 | 3 | 0 | 0 | 0 | 0
Store Details of Users |  |  |  | 3 | 1 | 1 | 5 | 0 | 1 | 0
Validate User Credentials |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 | 0 | 2
Personalized Profile
Store user session in and out |  |  |  | 3 | 5 | 5 | 1 | 1 | 1 | 0
Register For Course | 5
Store students registered |  |  |  | 8 | 6 | 0 | 0 | 0 | 0 | 0
List the courses he can register |  |  |  | 3 | 1 | 3 | 3 | 3 | 0 | 0
Validate If he has all pre-requisites |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1 | 0
Access Course Content | 8
Create a database |  |  |  | 9 | 4 | 2 | 2 | 1 | 1 | 0
Design User Interface |  |  |  | 6 | 6 | 3 | 3 | 3 | 1 | 1
Add a few courses |  |  |  | 6 | 2 | 8 | 8 | 1 | 0 | 1
Video page framework |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
Write Quizzes | 3
Create a dataabase |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1 | 1
Add Quizzes at every level |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9 | 0
Update his level based on score |  |  |  | 9 | 9 | 9 | 4 | 3 | 3 | 3
Store students performance |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0 | 1
Total |  |  |  | 67.5 | 51 | 43 | 30 | 17 | 18 | 9
Create a Sprint Backlog in Smartsheet